## Simple Gantt Chart - BLANK
PROJECT TITLE | Software Engineering Project
PROJECT MANAGER | Sandra Czernik
COMPANY NAME | CapyTec
DATE | 2021-02-16 | [5 empty] | feb | [9 empty] | march | [24 empty] | apr | [19 empty] | may
[7 empty] | 15 |  |  |  |  | 22 |  |  |  |  | 1 |  |  |  |  | 8 |  |  |  |  | 15 |  |  |  |  | 22 |  |  |  |  | 29 |  |  |  |  | 5 |  |  |  |  | 12 |  |  |  |  | 19 |  |  |  |  | 26 |  |  |  |  | 3 |  |  |  |  | 10 |  |  |  |  | 17
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0.1 | Team Meetings | Sandra C. |  |  | 33
1 | MISSION 1 - Project Management | Sandra C. | 2021-02-16 | 2021-03-05 | 17 | 100%
1.1 | Project Proposal | Sandra C. | 2021-02-16 | 2021-02-19 | 3 | 100%
1.2 | Skills Audit of the team | Sandra C. | 2021-02-17 | 2021-02-19 | 2 | 100%
1.3 | Team Code of Conduct | Sandra C. | 2021-02-22 | 2021-02-25 | 3 | 100%
1.4 | Risk Analysis | Sandra C. | 2021-02-25 | 2021-03-05 | 8 | 100%
1.4 | Quality Document | Sandra C. | 2021-02-27 | 29/02/2021 | 2 | 100%
2 | MISSION 2 - Requirement Analysis | Sandra C. | 2021-03-05 | 2021-03-23 | 14 | 100%
2.1 | A statement of purpose | Sandra C. | 2021-03-05 | 2021-03-06 | 1 | 100%
2.2.1 | UML Case Diagram 1 | Sandra C. | 2021-03-08 | 2021-03-10 | 2 | 100%
2.2.2 | UML Case Diagram 2 | Sandra C. | 2021-03-11 | 2021-03-14 | 3 | 100%
2.3.1 | Use Case Description 1 | Sandra C. | 2021-03-15 | 2021-03-16 | 1 | 100%
2.3.2 | Use Case Description 2 | Sandra C. | 2021-03-15 | 2021-03-16 | 1 | 100%
2.3.3 | Use Case Description 3 | Sandra C. | 2021-03-16 | 2021-03-19 | 3 | 100%
2.3.4 | Use Case Description 4 | Sandra C. | 2021-03-19 | 2021-03-23 | 4 | 100%
3 | MISSION 3 - Software Analysis | Group | 2021-03-24 | 2021-04-16 | 23 | 100%
3.1 | Class Diagram | Group | 2021-03-24 | 2021-04-16 | 23 | 100%
3.2 | State Machine Diagrams | Group | 2021-03-25 | 2021-03-28 | 3 | 100%
3.2.1 | Sequence Diagrams | Group | 2021-03-28 | 2021-04-02 | 5 | 100%
3.2.2 | Activity Diagrams | Group | 2021-04-03 | 2021-04-09 | 6 | 100%
7 | MISSION 6 - Data Component | Alex H. | 2021-04-15 | 2021-05-22 | 37 | 100%
6.1 | Documentation of data model, ie Entity Relationship Diagram | Alex H. | 2021-04-15 | 2021-04-16 | 1 | 100%
6.1 | A method for persistent storage of data. | Alex H. | 2021-04-09 | 2021-04-16 | 7 | 100%
6.1 | Appropriate methods that allow other components to query and update the data | Alex H. | 2021-04-17 | 2021-05-22 | 35 | 100%
6 | GUI Creation | Group | 2021-04-17 | 2021-05-18 | 31 | 100%
6.1 | Creating GUI | Kieran R. | 2021-04-17 | 2021-04-20 | 3 | 100% | [47 empty] | . | . | . | . | . | . | . | . | .
6.1 | Task columns added to GUI | Kieran R. | 2021-05-04 | 2021-05-05 | 1 | 100%
5 | MISSION 5 - Task Entry Component | Kieran R. | 2021-05-18
5.1 | Functionality to allow appropriate users to add new regular and one-off tasks | Kieran R. | 2021-05-18 | 2021-05-19 | 1 | 100% | [58 empty] | . | . | . | . | . | . | . | .
5.2 | Allow user to add info such as tasks including duration, importance and frequency | Kieran R. | 2021-05-18 | 2021-05-19 | 1 | 100%
5.4 | Functionality to present a sortable lists of existing tasks | Kieran R. | 2021-05-19 | 2021-05-20 | 1 | 100%
5.1 | Fuinctionality to allow the user to select and edit task information | Kieran R. | 2021-05-19 | 2021-05-20 | 1 | 100%
5.1 | Undo Features | Kieran R. | 2021-05-19 | 2021-05-20 | 1 | 100%
5.3 | Safeguards against common errors, such as unnecessary duplicate tasks or tasks | Kieran R. | 2021-05-21 | 2021-05-22 | 1 | 100%
5.1 | User Guidance | Kieran R. | 2021-05-21 | 2021-05-22 | 1 | 100%
7 | MISSION 7 - Task Allocation Component | Kieran R. | 2021-05-18
7.1 | Functionality to allow assign tasks to caretakers allowing for expected time taken, preferences, individual talents and special conditions. | Kieran R. | 2021-05-18 | 2021-05-19 | 1 | 100%
7.2 | Functionality to provide a clear statement of daily tasks to each caretaker | Kieran R. | 2021-05-18 | 2021-05-19 | 1 | 100%
7.3 | Safeguards to prevent common errors, such as the same task being assigned twice. | Kieran R. | 2021-05-18 | 2021-05-19 | 1 | 100%
7.4 | Functionality to provide a sortable list of tasks, clearly indicating tasks that have not been assigned, as well as other key information such as task priority. | Kieran R. | 2021-05-19 | 2021-05-20 | 1 | 100%
7.5 | Undo Features | Kieran R. | 2021-05-19 | 2021-05-20 | 1 | 100%
7.6 | User Guidance | Kieran R. | 2021-05-21 | 2021-05-22 | 1 | 100%
8 | MISSION 8 - User Account Component | Alex H. | 2021-05-16 | 2021-05-23
8.1 | Functionality for adding new users to the system. | Alex H. | 2021-05-16 | 2021-05-17 | 1 | 100%
8.2 | Functionality for removing users from the system. | Alex H. | 2021-05-17 | 2021-05-18 | 1 | 100%
8.3 | Functionality for editing user information. | Alex H. | 2021-05-17 | 2021-05-18 | 1 | 100%
8.4 | Functionality to provide a way for users to log on, or otherwise securely indicate their identity. | Alex H. | 2021-05-20 | 2021-05-21 | 1 | 100%
8.5 | Functionality for categorisation of users with appropriate access features. | Alex H. | 2021-05-22 | 2021-05-23 | 1 | 100%
8.6 | Software interfaces that provide information to other components when they need to know the identity of the current user. | Alex H.
8.7 | Functionality to allow users to update security information such as passwords. | Alex H.
9 | MISSION 9 - Task Logging Component | Sam F. | 2021-05-05 | 2021-05-22 |  | 100%
9.1 | Functionality to allow caretakers to log the completion of certain regular and one-off tasks, including key information such as who completed the task, the time and additional comments. | Sam F. | 2021-05-05 | 2021-05-06 | 1 | 100% | [59 empty] | . | . | . | . | . | . | .
9.2 | Functionality allow caretakers to easily find tasks assigned to them, either completed or pending. This allows caretakers to quickly log task completion and identify tasks that are close to the deadline (or past the deadline.) | Sam F. | 2021-05-18 | 2021-05-19 | 1 | 100%
9.3 | Functionality to allow caretakers and managers to edit the record of tasks completed. | Sam F. | 2021-05-21 | 2021-05-22 | 1 | 100% | [68 empty] | .
10 | MISSION 10 - Reporting Component | Sam F. | 2021-05-19 | 2021-05-21 | 2 | 100%
10.1 | Functionality to provide reports on the current status of tasks, particularly overdue tasks. | Sam F. | 2021-05-19 | 2021-05-20 | 1 | 100%
10.2 | Functionality to provide reports on the historic performance of the caretakers, particularly signs of poor performance or unequal workload. | Sam F. | 2021-05-20 | 2021-05-21 | 1 | 100%
10.3 | Functionality to provide reports on the historic completion of tasks, particularly tasks that are often overdue or not completed satisfactorily. | Sam F.
4 | MISSION 4 - Testing | Group | 2021-05-03 | 2021-05-23 | 20 | 100%
4.1 | Producing a process for testing | Group | 2021-05-03 | 2021-05-05 | 2 | 100%
4.2 | Full record of process in use | Group | 2021-05-22 | 2021-05-23 | 1 | 100%
Note on K10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This meeting occured earlier in the week as we wanted to complete [1.1] and [1.2] before the usual Friday's meeting time. Reply: Meeting notes: - creation of skills audits - came up with skills for the group for task 2 Notes: - Completion of both [1.1 and 1.2] into a PDF ready to be sent off - also discussed allocating missions and all gave opinions on who should do what mission
Note on O10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Microsoft Teams meeting, discussed what we will need to complete next, aka the code of conduct and a start on the risk analysis
Note on R10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting with all team members. Decided to relax with SEP work to focus on first Intelligent Systems Assignments
Note on S10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Crunch time for Intelligent Systems first assignment
Note on W10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Discussed how risk analysis and code of conduct were completed, and the statment of the purpose of the system. Next week goals: UML case diagrams and descriptions and a start on class diagrams if possible.
Note on Y10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Microsoft teams meeting, discussed what has been completed and what needs to be completed next, aka use case diagrams and descriptions
Note on AR10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting was help on Monday instead of last Friday, due to some team members not being able to attend because of family. Reply: 17:00 - 18:06
Note on AV10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20:02 - 20:14
Note on AX10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated class diagram during 1 hour meeting 19:50 - 20:42
Note on BA10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Meeting was help on Sunday 18th, as team members were busy on Friday and Saturday. Database was finalised on this day and now it will only recieve updates as new features are added which will be documented.
Note on BF10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 19:00-20:00 Reply: Discussed database and other missions that need to be started soon.
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both [1.1 Project Proposal] and [1.2 Skills Audit of the Team] were handed in this week
Note on M13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Both [1.1 Project Proposal] and [1.2 Skills Audit of the Team] were handed in this week
Note on N14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Code of conduct was completed in 3 days and approved by all team members.
Note on Q15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Risk analysis took 8 days to complete. This analysis includes a risk matrix in an excel spreadsheet and has been shared on One Drive with other team members Reply: Due to a busy schedule, with the first Intelligent Systems assignment being due soon, this risk analysis took a little longer than expected.
Note on X18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A statement of purpose has been completed, and included in our shared OneDrive.
Note on Y19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1st use case diagram has been completed in 2 days.
Note on AB20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2nd use case diagram has been completed in 3 days.
Note on AF21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use case description 1 and 2 were completed on the same day, the duration was 1 day.
Note on AF22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Use case description 1 and 2 were completed on the same day, the duration was 1 day.
Note on AG23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This use case description took 3 days to complete, as the task owner has been busy with other modules.
Note on AH24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This last use case description took 4 days to complete due to other modules.
Note on AJ26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The first version of the class diagram was completed early, but is being constantly adjusted to mtach the written code the other team members are producing. Reply: As this is a group mission, it will take longer as all team members need to be present to complete the work
Note on AZ31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Entity relationship diagram has been completed in 2 days by Alex
Note on AV32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Alex has completed the database component and uploaded to github by 16th.